## MVP scope
Summary | Issue key | Issue id | Issue Type | Status | Project key | Project name | Project type | Project lead | Project lead id | Project description | Priority | Resolution | Assignee | Assignee Id | Reporter | Reporter Id | Creator | Creator Id | Created | Updated | Last Viewed | Resolved | Due date | Votes | Description | Environment | Watchers | Watchers Id | Original estimate | Remaining Estimate | Time Spent | Work Ratio | Î£ Original Estimate | Î£ Remaining Estimate | Î£ Time Spent | Security Level | Custom field (Category) | Custom field (Development) | Custom field (Rank) | Custom field (Start date) | Status Category
As a dog owner, I want to browse and filter nearby dog walkers based on their ratings, reviews, prices, and schedules so that I can choose the best one for my dog. | DOG-1 | 10000 | Task | To Do | DOG | DogWalkerMVP | business | Amin Mraidi | 600c3f35be0f980076f93d9c |  | Highest |  |  |  | Amin Mraidi | 600c3f35be0f980076f93d9c | Amin Mraidi | 600c3f35be0f980076f93d9c | 2023-04-30 17:03 | 2023-04-30 22:18 | 2023-04-30 22:22 |  |  | 0 |  |  | Amin Mraidi | 600c3f35be0f980076f93d9c | [8 empty] | user story |  | 0¦hzzzzz: |  | To Do
As a dog walker, I want to be able to receive booking requests and accept or decline them based on my availability and preferences. | DOG-6 | 10005 | Task | To Do | DOG | DogWalkerMVP | business | Amin Mraidi | 600c3f35be0f980076f93d9c |  | High |  |  |  | Amin Mraidi | 600c3f35be0f980076f93d9c | Amin Mraidi | 600c3f35be0f980076f93d9c | 2023-04-30 19:49 | 2023-04-30 22:18 | 2023-04-30 22:32 |  |  | 0 |  |  | Amin Mraidi | 600c3f35be0f980076f93d9c | [8 empty] | user story |  | 0¦i0000f: |  | To Do
As a dog owner, I want to be able to book a dog walker for a specific time and date. | DOG-5 | 10004 | Task | To Do | DOG | DogWalkerMVP | business | Amin Mraidi | 600c3f35be0f980076f93d9c |  | High |  |  |  | Amin Mraidi | 600c3f35be0f980076f93d9c | Amin Mraidi | 600c3f35be0f980076f93d9c | 2023-04-30 19:37 | 2023-04-30 22:18 | 2023-04-30 19:38 |  |  | 0 |  |  | Amin Mraidi | 600c3f35be0f980076f93d9c | [8 empty] | user story |  | 0¦i00007: |  | To Do
As a dog owner, I want to rate and review the dog walker after the walk so that I can provide feedback and help other users. | DOG-7 | 10006 | Task | To Do | DOG | DogWalkerMVP | business | Amin Mraidi | 600c3f35be0f980076f93d9c |  | Medium |  |  |  | Amin Mraidi | 600c3f35be0f980076f93d9c | Amin Mraidi | 600c3f35be0f980076f93d9c | 2023-04-30 19:50 | 2023-04-30 22:18 | 2023-04-30 22:32 |  |  | 0 |  |  | Amin Mraidi | 600c3f35be0f980076f93d9c | [8 empty] | user story |  | 0¦i0000n: |  | To Do
As a dog walker, I want to create a profile for myself and specify my availability, preferences, and prices. | DOG-8 | 10007 | Task | To Do | DOG | DogWalkerMVP | business | Amin Mraidi | 600c3f35be0f980076f93d9c |  | Low |  |  |  | Amin Mraidi | 600c3f35be0f980076f93d9c | Amin Mraidi | 600c3f35be0f980076f93d9c | 2023-04-30 19:50 | 2023-04-30 22:18 | 2023-04-30 22:28 |  |  | 0 |  |  | Amin Mraidi | 600c3f35be0f980076f93d9c | [8 empty] | user story |  | 0¦i0000v: |  | To Do