## tasks
Summary | Issue key | Issue id | Issue Type | Status | Project key | Project name | Project type | Project lead | Project lead id | Project description | Priority | Resolution | Assignee | Assignee Id | Reporter | Reporter Id | Creator | Creator Id | Created | Updated | Last Viewed | Resolved | Due date | Votes | Description | Environment | Watchers | Watchers Id | Original estimate | Remaining Estimate | Time Spent | Work Ratio | Î£ Original Estimate | Î£ Remaining Estimate | Î£ Time Spent | Security Level | Custom field (Category) | Custom field (Development) | Custom field (Rank) | Custom field (Start date) | Parent | Parent summary | Status Category
Display listing after fixing a specific location and time | DOG-16 | 10015 | Sub-task | To Do | DOG | DogWalkerMVP | business | Amin Mraidi | 600c3f35be0f980076f93d9c |  | Highest |  |  |  | Amin Mraidi | 600c3f35be0f980076f93d9c | Amin Mraidi | 600c3f35be0f980076f93d9c | 2023-04-30 20:47 | 2023-04-30 22:19 | 2023-04-30 22:29 |  |  | 0 |  |  | Amin Mraidi | 600c3f35be0f980076f93d9c | [8 empty] | task |  | 0¦i0002n: |  | 10000 | As a dog owner, I want to browse and filter nearby dog walkers based on their ratings, reviews, prices, and schedules so that I can choose the best one for my dog. | To Do
Design a list and a text box UI to preform searches and display listings | DOG-14 | 10013 | Sub-task | To Do | DOG | DogWalkerMVP | business | Amin Mraidi | 600c3f35be0f980076f93d9c |  | Highest |  |  |  | Amin Mraidi | 600c3f35be0f980076f93d9c | Amin Mraidi | 600c3f35be0f980076f93d9c | 2023-04-30 20:42 | 2023-04-30 22:20 | 2023-04-30 22:29 |  |  | 0 |  |  | Amin Mraidi | 600c3f35be0f980076f93d9c | [8 empty] | task |  | 0¦i00027: |  | 10000 | As a dog owner, I want to browse and filter nearby dog walkers based on their ratings, reviews, prices, and schedules so that I can choose the best one for my dog. | To Do
Create a database schema to store booking requests and associated information | DOG-31 | 10030 | Sub-task | To Do | DOG | DogWalkerMVP | business | Amin Mraidi | 600c3f35be0f980076f93d9c |  | High |  |  |  | Amin Mraidi | 600c3f35be0f980076f93d9c | Amin Mraidi | 600c3f35be0f980076f93d9c | 2023-04-30 22:14 | 2023-04-30 22:21 | 2023-04-30 22:29 |  |  | 0 |  |  | Amin Mraidi | 600c3f35be0f980076f93d9c | [8 empty] | task |  | 0¦i0005r: |  | 10004 | As a dog owner, I want to be able to book a dog walker for a specific time and date. | To Do
AddÂ functionalityÂ forÂ dogÂ walkersÂ toÂ acceptÂ orÂ declineÂ bookingÂ requests | DOG-27 | 10026 | Sub-task | To Do | DOG | DogWalkerMVP | business | Amin Mraidi | 600c3f35be0f980076f93d9c |  | High |  |  |  | Amin Mraidi | 600c3f35be0f980076f93d9c | Amin Mraidi | 600c3f35be0f980076f93d9c | 2023-04-30 22:11 | 2023-04-30 22:24 | 2023-04-30 22:29 |  |  | 0 |  |  | Amin Mraidi | 600c3f35be0f980076f93d9c | [8 empty] | task |  | 0¦i00053: |  | 10005 | As a dog walker, I want to be able to receive booking requests and accept or decline them based on my availability and preferences. | To Do
Build a dashboard that displays new and upcoming booking requests | DOG-26 | 10025 | Sub-task | To Do | DOG | DogWalkerMVP | business | Amin Mraidi | 600c3f35be0f980076f93d9c |  | High |  |  |  | Amin Mraidi | 600c3f35be0f980076f93d9c | Amin Mraidi | 600c3f35be0f980076f93d9c | 2023-04-30 22:10 | 2023-04-30 22:22 | 2023-04-30 22:29 |  |  | 0 |  |  | Amin Mraidi | 600c3f35be0f980076f93d9c | [8 empty] | task |  | 0¦i0004v: |  | 10005 | As a dog walker, I want to be able to receive booking requests and accept or decline them based on my availability and preferences. | To Do
Store ratings in a database | DOG-20 | 10019 | Sub-task | To Do | DOG | DogWalkerMVP | business | Amin Mraidi | 600c3f35be0f980076f93d9c |  | High |  |  |  | Amin Mraidi | 600c3f35be0f980076f93d9c | Amin Mraidi | 600c3f35be0f980076f93d9c | 2023-04-30 20:56 | 2023-04-30 22:23 | 2023-04-30 22:29 |  |  | 0 |  |  | Amin Mraidi | 600c3f35be0f980076f93d9c | [8 empty] | task |  | 0¦i0003j: |  | 10006 | As a dog owner, I want to rate and review the dog walker after the walk so that I can provide feedback and help other users. | To Do
Selecting an item from the listing starts the booking proccess | DOG-17 | 10016 | Sub-task | To Do | DOG | DogWalkerMVP | business | Amin Mraidi | 600c3f35be0f980076f93d9c |  | High |  |  |  | Amin Mraidi | 600c3f35be0f980076f93d9c | Amin Mraidi | 600c3f35be0f980076f93d9c | 2023-04-30 20:52 | 2023-04-30 22:20 | 2023-04-30 22:29 |  |  | 0 |  |  | Amin Mraidi | 600c3f35be0f980076f93d9c | [8 empty] | task |  | 0¦i0002v: |  | 10000 | As a dog owner, I want to browse and filter nearby dog walkers based on their ratings, reviews, prices, and schedules so that I can choose the best one for my dog. | To Do
Store user information in a secure database. | DOG-10 | 10009 | Sub-task | To Do | DOG | DogWalkerMVP | business | Amin Mraidi | 600c3f35be0f980076f93d9c |  | High |  |  |  | Amin Mraidi | 600c3f35be0f980076f93d9c | Amin Mraidi | 600c3f35be0f980076f93d9c | 2023-04-30 20:35 | 2023-04-30 22:25 | 2023-04-30 22:29 |  |  | 0 |  |  | Amin Mraidi | 600c3f35be0f980076f93d9c | [8 empty] | task |  | 0¦i0001b: |  | 10007 | As a dog walker, I want to create a profile for myself and specify my availability, preferences, and prices. | To Do
Design a booking form for dog owners to specify their requirements | DOG-30 | 10029 | Sub-task | To Do | DOG | DogWalkerMVP | business | Amin Mraidi | 600c3f35be0f980076f93d9c |  | Medium |  |  |  | Amin Mraidi | 600c3f35be0f980076f93d9c | Amin Mraidi | 600c3f35be0f980076f93d9c | 2023-04-30 22:13 | 2023-04-30 22:21 | 2023-04-30 22:29 |  |  | 0 |  |  | Amin Mraidi | 600c3f35be0f980076f93d9c | [8 empty] | task |  | 0¦i0005j: |  | 10004 | As a dog owner, I want to be able to book a dog walker for a specific time and date. | To Do
Develop a notification system to alert dog walkers when a new booking request is made | DOG-24 | 10023 | Sub-task | To Do | DOG | DogWalkerMVP | business | Amin Mraidi | 600c3f35be0f980076f93d9c |  | Medium |  |  |  | Amin Mraidi | 600c3f35be0f980076f93d9c | Amin Mraidi | 600c3f35be0f980076f93d9c | 2023-04-30 22:09 | 2023-04-30 22:22 | 2023-04-30 22:29 |  |  | 0 |  |  | Amin Mraidi | 600c3f35be0f980076f93d9c | [8 empty] | task |  | 0¦i0004f: |  | 10005 | As a dog walker, I want to be able to receive booking requests and accept or decline them based on my availability and preferences. | To Do
Integrate and display the rating and review into the dog walker's profile page | DOG-21 | 10020 | Sub-task | To Do | DOG | DogWalkerMVP | business | Amin Mraidi | 600c3f35be0f980076f93d9c |  | Medium |  |  |  | Amin Mraidi | 600c3f35be0f980076f93d9c | Amin Mraidi | 600c3f35be0f980076f93d9c | 2023-04-30 20:57 | 2023-04-30 22:21 | 2023-04-30 22:29 |  |  | 0 |  |  | Amin Mraidi | 600c3f35be0f980076f93d9c | [8 empty] | task |  | 0¦i0003r: |  | 10006 | As a dog owner, I want to rate and review the dog walker after the walk so that I can provide feedback and help other users. | To Do
Display review form at the end of a walk | DOG-19 | 10018 | Sub-task | To Do | DOG | DogWalkerMVP | business | Amin Mraidi | 600c3f35be0f980076f93d9c |  | Medium |  |  |  | Amin Mraidi | 600c3f35be0f980076f93d9c | Amin Mraidi | 600c3f35be0f980076f93d9c | 2023-04-30 20:56 | 2023-04-30 22:21 | 2023-04-30 22:29 |  |  | 0 |  |  | Amin Mraidi | 600c3f35be0f980076f93d9c | [8 empty] | task |  | 0¦i0003b: |  | 10006 | As a dog owner, I want to rate and review the dog walker after the walk so that I can provide feedback and help other users. | To Do
Display rating on profiles | DOG-13 | 10012 | Sub-task | To Do | DOG | DogWalkerMVP | business | Amin Mraidi | 600c3f35be0f980076f93d9c |  | Medium |  |  |  | Amin Mraidi | 600c3f35be0f980076f93d9c | Amin Mraidi | 600c3f35be0f980076f93d9c | 2023-04-30 20:38 | 2023-04-30 20:39 | 2023-04-30 22:29 |  |  | 0 |  |  | Amin Mraidi | 600c3f35be0f980076f93d9c | [8 empty] | task |  | 0¦i0001z: |  | 10007 | As a dog walker, I want to create a profile for myself and specify my availability, preferences, and prices. | To Do
Allows users to set pricing options | DOG-12 | 10011 | Sub-task | To Do | DOG | DogWalkerMVP | business | Amin Mraidi | 600c3f35be0f980076f93d9c |  | Medium |  |  |  | Amin Mraidi | 600c3f35be0f980076f93d9c | Amin Mraidi | 600c3f35be0f980076f93d9c | 2023-04-30 20:37 | 2023-04-30 20:39 | 2023-04-30 22:29 |  |  | 0 |  |  | Amin Mraidi | 600c3f35be0f980076f93d9c | [8 empty] | task |  | 0¦i0001r: |  | 10007 | As a dog walker, I want to create a profile for myself and specify my availability, preferences, and prices. | To Do
Develop a registration form with fields for necessary information such as name, email, and password. | DOG-9 | 10008 | Sub-task | To Do | DOG | DogWalkerMVP | business | Amin Mraidi | 600c3f35be0f980076f93d9c |  | Medium |  |  |  | Amin Mraidi | 600c3f35be0f980076f93d9c | Amin Mraidi | 600c3f35be0f980076f93d9c | 2023-04-30 20:34 | 2023-04-30 20:36 | 2023-04-30 22:29 |  |  | 0 |  |  | Amin Mraidi | 600c3f35be0f980076f93d9c | [8 empty] | task |  | 0¦i00013: |  | 10007 | As a dog walker, I want to create a profile for myself and specify my availability, preferences, and prices. | To Do
Cancels all other bookings when one dog walker was selected for a dog owner | DOG-33 | 10032 | Sub-task | To Do | DOG | DogWalkerMVP | business | Amin Mraidi | 600c3f35be0f980076f93d9c |  | Low |  |  |  | Amin Mraidi | 600c3f35be0f980076f93d9c | Amin Mraidi | 600c3f35be0f980076f93d9c | 2023-04-30 22:16 | 2023-04-30 22:21 | 2023-04-30 22:17 |  |  | 0 |  |  | Amin Mraidi | 600c3f35be0f980076f93d9c | [8 empty] | task |  | 0¦i0005z: |  | 10004 | As a dog owner, I want to be able to book a dog walker for a specific time and date. | To Do
Design a calendar interface to allow dog walkers to set their availability | DOG-32 | 10031 | Sub-task | To Do | DOG | DogWalkerMVP | business | Amin Mraidi | 600c3f35be0f980076f93d9c |  | Low |  |  |  | Amin Mraidi | 600c3f35be0f980076f93d9c | Amin Mraidi | 600c3f35be0f980076f93d9c | 2023-04-30 22:15 | 2023-04-30 22:26 | 2023-04-30 22:29 |  |  | 0 |  |  | Amin Mraidi | 600c3f35be0f980076f93d9c | [8 empty] | task |  | 0¦i00023: |  | 10007 | As a dog walker, I want to create a profile for myself and specify my availability, preferences, and prices. | To Do
Build a notification system to alert dog owners when their booking request has been accepted or declined | DOG-28 | 10027 | Sub-task | To Do | DOG | DogWalkerMVP | business | Amin Mraidi | 600c3f35be0f980076f93d9c |  | Low |  |  |  | Amin Mraidi | 600c3f35be0f980076f93d9c | Amin Mraidi | 600c3f35be0f980076f93d9c | 2023-04-30 22:11 | 2023-04-30 22:23 | 2023-04-30 22:29 |  |  | 0 |  |  | Amin Mraidi | 600c3f35be0f980076f93d9c | [8 empty] | task |  | 0¦i0005b: |  | 10005 | As a dog walker, I want to be able to receive booking requests and accept or decline them based on my availability and preferences. | To Do
Allow dog walkers to finalize a walk, prompts both owner and walker | DOG-18 | 10017 | Sub-task | To Do | DOG | DogWalkerMVP | business | Amin Mraidi | 600c3f35be0f980076f93d9c |  | Low |  |  |  | Amin Mraidi | 600c3f35be0f980076f93d9c | Amin Mraidi | 600c3f35be0f980076f93d9c | 2023-04-30 20:55 | 2023-04-30 22:23 | 2023-04-30 22:29 |  |  | 0 |  |  | Amin Mraidi | 600c3f35be0f980076f93d9c | [8 empty] | task |  | 0¦i00033: |  | 10006 | As a dog owner, I want to rate and review the dog walker after the walk so that I can provide feedback and help other users. | To Do
Allow for filtering by price, ratings, and distance | DOG-15 | 10014 | Sub-task | To Do | DOG | DogWalkerMVP | business | Amin Mraidi | 600c3f35be0f980076f93d9c |  | Low |  |  |  | Amin Mraidi | 600c3f35be0f980076f93d9c | Amin Mraidi | 600c3f35be0f980076f93d9c | 2023-04-30 20:43 | 2023-04-30 22:19 | 2023-04-30 22:29 |  |  | 0 |  |  | Amin Mraidi | 600c3f35be0f980076f93d9c | [8 empty] | task |  | 0¦i0002f: |  | 10000 | As a dog owner, I want to browse and filter nearby dog walkers based on their ratings, reviews, prices, and schedules so that I can choose the best one for my dog. | To Do
Allows users to set their availability in real-time | DOG-11 | 10010 | Sub-task | To Do | DOG | DogWalkerMVP | business | Amin Mraidi | 600c3f35be0f980076f93d9c |  | Low |  |  |  | Amin Mraidi | 600c3f35be0f980076f93d9c | Amin Mraidi | 600c3f35be0f980076f93d9c | 2023-04-30 20:36 | 2023-04-30 22:25 | 2023-04-30 22:29 |  |  | 0 |  |  | Amin Mraidi | 600c3f35be0f980076f93d9c | [8 empty] | task |  | 0¦i0001j: |  | 10007 | As a dog walker, I want to create a profile for myself and specify my availability, preferences, and prices. | To Do