## Sheet1
MVP Scope | Subtask | Implemented Yes/No | Note
1. Browse and filter nearby dog walkers | Display listing after fixing a specific location and time | Partially | Completes the required list display, but does not filter by time and location.Completed 50%
| Design a list and a text box UI to perform searches and display listings | Yes
| Allow for filtering by price, ratings, and distance | Partially | Completed most of the requirements, except for filtering by distance.Completed 70%
| Selecting an item from the listing starts the booking process | Yes
2. Receive and manage booking requests | Develop a notification system to alert dog walkers of new booking requests | Yes
| Build a dashboard that displays new and upcoming booking requests | Yes
| Add functionality for dog walkers to accept or decline booking requests | Yes
| Build a notification system to alert dog owners of booking request status | Yes
3. Rate and review dog walkers | Allow dog walkers to finalize a walk and prompt for reviews | Yes
| Display review form at the end of a walk | Yes
| Store ratings in a database | Yes
| Integrate and display rating and reviews on dog walker profiles | Yes
4. Create dog walker profile | Develop a registration form with necessary information fields | Yes
| Store user information in a secure database | Yes
| Allow users to set availability in real-time | Yes
| Allow users to set pricing options | Yes
| Display rating on profiles | Yes
5. Book a dog walker | Design a booking form for dog owners to specify requirements | Yes
| Create a database schema to store booking requests and associated information | Yes
| Cancel all other bookings when one dog walker is selected | Yes
MVP realization ratio=(Number of completed subtasks * Completion of subtasks / Total number of subtasks) * 100 | ≈ 93.84%